Select any team name you prefer.
Please enter your name as it appears in Canvas.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This is the sprint during which the grader will grade your implementation of this feature.

By the END of this sprint, you must have implemented this feature.

If this field is blank, then this is a bonus feature. If implemented, it will be graded after the final sprint for extra credit.
This is the MAXIMUM number of bonus points awarded if you successfully and completely implement this feature.

If blank, this feature is REQUIRED. You MAY NOT work on ANY bonus feature until ALL required features have been implemented.

If non-blank, some or all bonus points will be awarded ONLY if the feature is COMPLETELY implemented.
 Complete but non-optimal implementations may receive partial credit.
Incomplete or nearly-complete implementations will receive no bonus points.
This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point feature).

In a real project, points are assigned via a game of "estimating poker" played by the entire team.
This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point feature).

In a real project, points are assigned via a game of "estimating poker" played by the entire team.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any features not planned for the current sprint.

If you planned a "full credit" feature for the current sprint but don't complete it, then just update this cell for the next sprint. This will only affect your grade if this feature was *required* to be completed by a specific sprint, and is not.

If you planned a "bonus" or "extreme bonus" feature for the current sprint but don't complete it, and you don't want to use it for the next sprint, just use the Delete key to leave this cell blank. Your "full credit" grade will not be penalized for this decision.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO SHIP.
    "Finished in Sprint 1" means it was delivered at the end of Sprint 1.
    "Finished in Sprint 2" - "Finished in Sprint 6" are the same for those sprints.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that no duplicate work occurs, and that no tasks "fall through the cracks".

If you are wroking individually, you do NOT need to put your initials next to every task. We'll figure out who did the work. Somehow.
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the manual to cover this feature", or "Fix the seg fault bug".

Expect roughly 3 to 10 tasks per typical feature. Don't OVER plan, but also don't just write "Implement the feature". Find a middle ground. :-)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
## Product Backlog
Project Name	Mavs Arboreta, Nursery, and Garden Association (MANGA)
Product Name:						Complete Fields in Green!!!
Team ID:						Product Backlog Burn Chart / Sprints / Features Remaining at end of Sprint

	Team Member Name					Initials	Student ID
Required

Sprint #	Remaining	Completed This Sprint				Comment
0	30				Total	Total number of features (in column H)
1	25	5			1	Total features left at the end of Sprint #1
2	25	0			2	Total features left at the end of Sprint #2
3	25	0			3	...and so on
4	25	0
5	25	0
6	25	0

©2016-2020 by George F. Rice
This work is licensed under a Creative Commons Attribution 4.0 International License.						Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
						Additional features may be proposed by the student but must be approved by the Product Owner in writing
						Features
Feature ID	Priority	Required	Bonus	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
STORE	1	1		13	1	Finished in Sprint 1	Manager	Create an empty store (via CLI)	Open new branches and franchises	Need a Store class and a simple main()
TOOL	2	1		8	1	Finished in Sprint 1	Inventory	Add a Tool product to the store (via CLI)	Add new products to sell	Need a Product base class and trivial Tool derived class
LISTPROD	3	1		5	1	Finished in Sprint 1	Sales Staff	List all products in the store (via CLI)	Find products my customers need	Simple iteration loop
PLANT	4	1		5	1	Finished in Sprint 1	Inventory	Add a Plant product to the store (via CLI)	Add new products to sell	Simple derived class and additional menu item
MULCH	5	1		5	1	Finished in Sprint 1	Inventory	Add a Mulch product to the store (via CLI)	Add new products to sell	Simple derived class and additional menu item
WINDOW	6	2		13			Manager	Create a main window for the store	Use the software more easily	Recommend baselining Nim from Lecture 13
TOOLW	7	2		8			Inventory	Add New Tool series of dialogs to add Tool product	More easily create new Tools	Recommend baselining EntryDialog from Lecture 14
LISTW	8	2		5			Sales Staff	List all products in the main window data area	Find products my customers need	Try using std::ostringstream to capture operator<< formatting
PLANTW	9	2		3			Inventory	Add New Plant dialogs	More easily create new Plants
MULCHW	10			3			Inventory	Add New Mulch dialogs	More easily create new Mulch products
SAVE	11	3		13			Manager	Save all products to untitled.manga	Avoid rekeying all data (!)	This requires modifying the “model” to save and reload each object from a provided stream
LOAD	12	3		8			Manager	Load saved products from a selected filename	Avoid rekeying all data (!)	Use Gtk::FileChooser
SAVEAS	13	3		8			Manager	Save as a specified / selected filename	Manage multiple stores	Use Gtk::FileChooser
ABOUT	14	3		1			Manager	Provide About dialog for documenting licenses	Avoid a lawsuit	Use Gtk::AboutDialog
CUSTOMER	15	4		21			Sales Staff	Create a new Customer via a unified dialog	Add a new customer	Will need a Customer class, a Store::_customers vector, and a dialog to create them
LISTCUST	16	4		8			Sales Staff	List all Customers in the main window data area	Find the current customer	Will need appropriate add and iterate methods for Store
STATUS	17	5					Manager	Add a status bar	Monitor program operation more clearly	Recommend a Gtk::Label and Mainwin methods to update and clear the status bar. Consider using Pango for more attractive status!
ORDER	18	5		21			Sales Staff	Create an Order	Sell stuff!	Will need an Order class, Store::_orders vector, and dialog to create them
LISTORD	19	5		5			Sales Staff	List all Orders (with cost) in the main data area	Find the order for a Customer
TOOLBAR	20	5		8			Sales Staff	Add a tool bar	Access program functions more easily	Include a functionality from main menu except exit and help
SORTCUST	21	6		8				Sort the Customer list by name
ITERATORS	22	6		13				REFACTOR: Use iterators with Store's vectors
						BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
UNIFIED	23		25	13			Sales Staff	Replace all remaining dialog sequences with unified dialogs each	Enter data more quickly
SCROLL	24		10	5			Customer	Make the main window’s data area scrollable	See large volumes of data	The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
DEPRECATE	25		25	13			Inventory	Deprecate a product	Avoid selling products that are out of production	This requires a Boolean with getter and setter in the Options and Desktop classes to indicate which are deprecated. The index number may pose interesting challenges, since deprecation will create gaps.
STATUS++	26		15	8			Manager	Replace the Gtk::Label for the status bar with Gtk::Statusbar, and maintain a message stack	Better track status of messages	Just swapping Gtk::Statusbar for Gtk::Label is trivial. Think through how to manage a first-in last-out stack of messages
RMPROD	27		25	13			Sales Staff	Remove a product from an order in progress	More quickly assist indecisive Customers
STATE	28		40	21			Manager	Track order state: pending, paid, complete	Collect metrics on order processing
EDITCUST	29		15	8			Sales Staff	Enable editing any Customer attribute(s)	Keep our CRM data up to date
EDITPROD	30		25	13			Inventory	Enable editing a Product's name, price, and description	More quickly track changes to our portfolio of products

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 06		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 13		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	17
Day 1 Left	12	5
Day 2 Left	8	4
Day 3 Left	7	1
Day 4 Left	7	0
Day 5 Left	4	3
Day 6 Left	4	0
Day 7 Left	0	4
			Note: Due to the late project start, the results of this sprint will be provided to you (although you may use your own solution if you prefer)
Task ID	Feature ID	Assigned To	Task	Status	Notes
1	TOOL		Write the Product class	Completed Day 1	Test each class and method as it is written
2	TOOL		Write operator<< for Product	Completed Day 1	Commit and push AT LEAST once every class or update
3	TOOL		Write Store::add_product, products, and product(int)	Completed Day 1
4	TOOL		Write the Options class sans to_string	Completed Day 1
5	TOOL		Write the Tool class	Completed Day 1
6	STORE		Write Store class	Completed Day 2
7	STORE		Write operator<< for Store	Completed Day 2
8	STORE		Write first draft of main() function – add Tools	Completed Day 2
9	LISTPROD		Update main() function to list Products (polymorphism should enable other products to list as well)	Completed Day 2
10	PLANT		Write Exposure enum class	Completed Day 3
11	PLANT		Write Exposure operator<< function	Completed Day 5
12	PLANT		Write Plant class	Completed Day 5
13	PLANT		Update main() function to create Plant products	Completed Day 5
14	MULCH		Write Material enum class	Completed Day 7
15	MULCH		Write Material operator<< function	Completed Day 7
16	MULCH		Write Mulch class	Completed Day 7
17	MULCH		Update main() function to create Mulch products	Completed Day 7
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Oct 13		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 20		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Oct 20		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 27		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Oct 27		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 03		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint #	5		Complete Fields in Green!!!
Start on	Nov 03		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 10		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint #	6		Complete Fields in Green!!!
Start on	Nov 10		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 17		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84